## About
ABOUT THIS GANTT CHART
Visualise and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Gantt Chart
Machine Learning-Based Star Classification Using GAIA Satellite Data
University of Sussex |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Jack Watson
Project Start Date: | 2024-09-23 |  |  |  |  | September | [13 empty] | October | [27 empty] | November
Scrolling Increment: | 0 | time axis 2024-09-23 to 2024-11-17
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-09-23 to 2024-11-17
Proposal
Prepare Project Idea | Low Risk |  | 100% | 2024-09-23 | 5
Confirm Supervisor | Milestone |  | 100% | 2024-10-03 | 1 | bar: 2024-10-03
Draft Project Proposal | Low Risk |  | 75% | 2024-10-08 | 11
Submission | Goal |  | 75% | 2024-10-18 | 1 | 2024-10-18: 2
Research
GAIA | Low Risk |  | 0% | 2024-10-13 | 6
Machine Learning Methods | Low Risk |  | 0% | 2024-10-13 | 6
Prepare Documentation | Med Risk |  | 10% | 2024-10-08 | 11
Interim Report
Introduction | High Risk |  | 0% | 2024-10-09 | 0
Profesional Considerations | On Track |  | 0% | 2024-10-11 | 0
Requirements Analysis | Low Risk |  | 0% | 2024-10-16 | 0
Project Plan | Milestone |  | 0% | 2024-10-18 | 0
Log | Low Risk |  | 0% | 2024-10-19 | 0
Submission | Goal |  | 0% | 2024-11-07 | 1 | 2024-11-07: 2
Code
Iteration 1 | Milestone |  | 0%
Final Report
Cover Sheet | Low Risk |  | 0% | 2024-09-23 | 0
Signed Statement | Low Risk |  | 0% | 2024-09-24 | 0
Acknowledgements | Low Risk |  | 0% | 2024-09-25 | 0
Summary | Low Risk |  | 0%
Table of Contents | Low Risk |  | 0%
Introduction | Low Risk |  | 0%
Professional Considerations | Med Risk |  | 0%
Body of Report | High Risk |  | 0%
Conclusion | Med Risk |  | 0%
References | Low Risk |  | 0%
Appendices | Low Risk |  | 0%
Submission | Goal |  | 0% | 2025-04-11
Presentation
Draft presentation | High Risk |  | 0%
Present | Goal |  | 0%
To add more data, Insert new rows ABOVE this one